## Sheet1
Week | Feature/Deliverable | Difficulty (Hard/Medium/Easy) | Importance (Must Have/Nice to Have) | Task type | Goals
week1 | Development setup | Medium | Must | Devops | Have to set up the development setup
week2 | Frontend design | Hard | Must | Frontend | Have to complete frontend design
week3 | Backend design | Hard | Must | Backend | Have to complete backend design
week4 | U.I implementation-1 | Hard | Must | Frontend | Start implementing U.I component-1
week5 | Backend implementation -1 | Hard | Must | Backend and integration | Implement backend for U.I complement-1
week6 | U.I-2 and Backend -2 | Hard | Must | Frontend,Backend and integration | Implement backend and U.I complement-2
week7 | U.I-3 and Backend -3 | Hard | Must | Frontend,Backend and integration | Implement backend and U.I complement-3
week8 | Testing | Hard | Must | Testing | Testing all components
week9 | Production setup | Hard | Must | Production | Deploy in production
week10 | Live | Hard | Must | Release | Product release